## Sheet1
Block | Schematic/RTL Design Time | Status | Comments | Owner | Floorplanning | Status | Starting 7th Sept
FVFCCII | 2.5 Days | Open | front end block | Anthony | N/A
Bias Current Generation Block | 2 Days | Open | PMOS Current Mirror + External R to GND ( Simulate This) | Anthony | N/A
FVF Gain Boosting Amplifier | 2 Days | Open |  | Anthony | N/A
FVF Simulations | 1.5 Days | Open |  | Anthony | N/A
FVF Doc / Results | 1 Day | Open |  | Anthony | N/A
Delay Cell / CCO | 5 Days | Open |  | Anthony | N/A
Delay Cell Simulations | 2 Days | Open |  | Anthony | N/A
CCO Doc / Results | 1 Day | Open |  | Anthony | N/A
Toplevel Sims | 2 Days | Open | This is building the testbenches - sims run continuously with more blocks + parasitics added as available | Anthony | N/A
Floorplan Chip/IO/Signals etc. | 1 Day | Open | Generate Abstracts with pin positions | Anthony | Danny
CCO Delay cell layout | 1 Week | Open | First version within 2 days, iterate to optimise parasitics | Anthony | Micheal/Cypress/Subhash
FVF Gain Boosting Amplifier Layout | 3 Days | Open |  | Anthony | N/A
Bias Generation Layout | 1 Day | Open |  | Anthony | N/A
Full FVF Layout | 4 Days | Open |  | Anthony | N/A
Phase Sampler | 2 Days | Open |  | Anthony | N/A
Phase Sampler Layout | 2 Days | Open | Run Extracted sims & check extracted performance (standard cells) | Anthony | N/A
Clock Squarer + Buffer | 5 Days | Open |  | Anthony | N/A
Clock Squarer + Buffer Layout | 3 Days | Open |  | Anthony | N/A
Clock Divider | 3 Days | Open | Plan to use standard cells | Anthony | N/A
Clock Divider Layout | 1 Day | Open | First divider critical | Anthony | N/A
Sinc Filter & Decimator | 3 Days | Open | Talk to Purushothaman for Advice | Anthony | Purushthaman
Synthesis / P&R | 3 Days | Open | Assume Scripts are set up correctly, get help from Ivan / Anita | Anthony | Anita/Purushothaman/Gerardo
IO | 2 Days | Open | Subhash Comp as template | Anthony | Subhash
IO Layout | 3 Days | Open | Assume modifying existing IO Ring | Anthony | Subhash
Low Leakage ESD Cell (Optional) | 2.5 Days | Open |  | Anthony
LL ESD Cell Layout (Optional) | 5 Days | Open | Might need to occupy area of two cells | Anthony
Toplevel Layout Hookup | 3 Days | Open |  | Anthony+Michael | Michael
Chip Finishing LVS+DRC Clean +Density | 5 Days | Open | Need Michael's Help with this task | Michael | Michael
Latchup compatibility/robustness |  | Open | Need Michael's Help with this task | Anthony | Michael

## Schedule
Task | Task Time | Owner | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31
Revise Previous Work | 1/3 Week
Read Paper(s) on Howland | 1/3 Week
Revise Noise, DACs, Filters | 1/3 Week
Previous Literature Review | 1 Week
Output Filter Topology, Specs & Modelling | 2 Weeks
Howland Pump Block Specs & Modelling | 1 Week
DAC & V-I Specs, Selection and Modelling | 1 Week
Filter Design & Simulation | 1 Week
Howland Pump Design & Simulation | 1 Week
Write Prelim Report | 1 Week
DAC & I-V Design & Simulation | 2 Weeks
Board Power Supply Design | 1 Week
Toplevel Schematics & PCB Design | 1 Week
Test Plan | 0.5 Week
DAC Driver Programming | 0.5 Week
Seminar Prep | 1 Week
Report Writing | 2 Weeks
[11 empty] | Prelim Report | Paper Design & MATLAB | Christmas |  | Schematic Design | Exams |  | PCB Design | PCB FAB | PCB FAB | ??Seminar?? | PCB FAB | PCB FAB | PCB FAB | PCB Test |  |  |  | ?? Final Report ?? |  |  | Final Exams